## PHobenGanttShart
Value Furniture
PHOBENS
P.Hoben
TASK NAME | ASSIGNED TO | START DATE | DUE DATE | DURATION | % DONE | DESCRIPTION | PRIORITY | SPRINT/MILESTONE
Stage 1: Planning | P.Hoben | 2019-06-01 | 2019-07-05 | 34 | 100 | Planning stage for the project | High | Phase 1
1.1.1 Questionnaires | P.Hoben | 2019-06-01 | 2019-06-14 | 13 | 100 | Questionnaires need to be sent out to the client. To collect details on the system requirements and functionality. | High | Phase 1
1.1.2 Planning Report | P.Hoben | 2019-06-04 | 2019-07-05 | 31 | 100 |  | High | Phase 1
1.1.2.1 Interpretation of the project assignment brief | P.Hoben | 2019-06-05 | 2019-06-06 | 1 | 100 | My opinon on what needs to be done for the project | High | Phase 1
1.1.2.2 Functional + Non-Function Req. | P.Hoben | 2019-06-07 | 2019-07-07 | 30 | 100 | Functional and non-function requirements of the system detailed | High | Phase 1
1.1.2.3 Top Level Use Case Model | P.Hoben | 2019-06-08 | 2019-06-12 | 4 | 100 | Use case diagram about the system created | High | Phase 1
1.1.2.4 Initial Class Diagram | P.Hoben | 2019-06-09 | 2019-06-10 | 1 | 100 | Initial class diagram detailing the classes that are needed for the system. | High | Phase 1
1.1.2.5 Background Research | P.Hoben | 2019-06-10 | 2019-06-18 | 8 | 100 | Research into the type of system that I am looking to develop | High | Phase 1
1.1.2.6 Aims of Project Assignment | P.Hoben | 2019-06-20 | 2019-06-22 | 2 | 100 | Aims of the project that I am intending to accomplish | High | Phase 1
1.1.2.7 Identify Resources, Materials | P.Hoben | 2019-06-28 | 2019-06-30 | 2 | 100 | Any resouces that will be used to complete this project | High | Phase 1
1.1.2.8 Identify Information Sources Used | P.Hoben | 2019-06-29 | 2019-06-30 | 1 | 100 | information to be used to complete the project | High | Phase 1
1.1.3 Project Plan | P.Hoben | 2019-06-01 | 2019-07-05 | 34 | 100 |  | High | Phase 1
1.1.3.1 Main Milestones | P.Hoben | 2019-07-01 | 2019-07-05 | 4 | 100 | Main objectives in the project to be Detailed in the Gantt Chart. | High | Phase 1
1.1.3.2 Breakdown of tasks in each stage | P.Hoben | 2019-07-02 | 2019-07-03 | 1 | 100 | List of the tasks needed to complete the project | High | Phase 1
1.1.3.3 Realistic Timescales Set | P.Hoben | 2019-07-02 | 2019-07-05 | 3 | 100 | Timescales set have to be achieveable | High | Phase 1
1.1.3.4 Scheduling of Tasks | P.Hoben | 2019-07-03 | 2019-07-05 | 2 | 100 | Tasks to be scheduled to fit time scale | High | Phase 1
1.1.3.5 Deliverable | P.Hoben | 2019-07-04 | 2019-07-05 | 1 | 100 | Deliverables need to be available | High | Phase 1
1.1.3.6 Resources Used | P.Hoben | 2019-07-04 | 2019-07-05 | 1 | 100 | Any resources used must be detailed | High | Phase 1
Stage 1.2: Analysis and Design | P.Hoben | 2019-07-05 | 2019-07-12 | 7 | 100 |  | High | Phase 2
1.2.1 Use Case Diagram | P.Hoben | 2019-07-08 | 2019-07-09 | 1 | 100 | Use case diagram for the system | High | Phase 2
1.2.2 Class Diagram Detailed | P.Hoben | 2019-07-09 | 2019-07-10 | 1 | 100 | Class diagram for the system | High | Phase 2
1.2.3 Activity Diagrams | P.Hoben | 2019-07-08 | 2019-07-09 | 1 | 100 | Activity diagrams for the system | High | Phase 2
1.2.4 Sequence Diagrams | P.Hoben | 2019-07-10 | 2019-07-11 | 1 | 100 | Sequence diagrams for the system | High | Phase 2
1.2.5 Normalization | P.Hoben | 2019-07-10 | 2019-07-11 | 1 | 100 | Normalization of order form | High | Phase 2
1.2.6 ER Diagram | P.Hoben | 2019-07-08 | 2019-07-09 | 1 | 100 | ER diagram for the system | High | Phase 2
1.2.7 Event Handling Forms | P.Hoben | 2019-07-08 | 2019-07-09 | 1 | 100 | Event handing forms for the system need to be created | High | Phase 2
1.2.8 Module Description | P.Hoben | 2019-07-10 | 2019-07-11 | 1 | 100 | Module desciption to be created | High | Phase 2
1.2.9 Screen Layouts Charts | P.Hoben | 2019-08-11 | 2019-08-12 | 1 | 100 | Screen layouts of system to be created | High | Phase 2
Stage 2: Development | P.Hoben | 2019-07-12 | 2019-07-20 | 8 | 100 |  | High | Phase 3
2.1 Implementation | P.Hoben | 2019-07-12 | 2019-07-13 | 1 | 100 |  | High | Phase 3
2.1.1 Setting Up of IDE and Project | P.Hoben | 2019-07-13 | 2019-07-14 | 1 | 100 | Set up Visual Studio with any essential extensions added and Updates applied | High | Phase 3
2.1.2 Creating POCO Classes | P.Hoben | 2019-07-13 | 2019-07-15 | 2 | 100 | Creating POCO classes | High | Phase 3
2.1.3 Constructing Administration Pages | P.Hoben | 2019-07-15 | 2019-07-16 | 1 | 100 | Creating admin pages for all the admin functionality. | High | Phase 3
2.1.4 Constructing User Pages | P.Hoben | 2019-07-16 | 2019-07-18 | 2 | 100 | Creating user pages so the users can access certain areas | High | Phase 3
2.1.5 Constructing Homepage and product information pages | P.Hoben | 2019-07-16 | 2019-07-19 | 3 | 100 | Creating the homepage and the product pages | High | Phase 3
2.1.6 Construct a shopping cart system | P.Hoben | 2019-07-16 | 2019-07-19 | 3 | 100 | Creating the shopping cart page and functionality |  | Phase 3
2.2 Testing | P.Hoben | 2019-07-14 | 2019-07-20 | 6 | 100 |  | High | Phase 4
2.2.1 Test Strategy | P.Hoben | 2019-07-16 | 2019-07-17 | 1 | 100 | Creating a strategy to use for the testing | High | Phase 4
2.2.2 List of Test Cases | P.Hoben | 2019-07-18 | 2019-07-19 | 1 | 100 | List of the test cases | High | Phase 4
2.2.3 Completed Test Data, Expected Results & Results | P.Hoben | 2019-07-18 | 2019-07-20 | 2 | 100 | Record all the testing data | High | Phase 4
2.2.4 Print Screen Layouts | P.Hoben | 2019-07-19 | 2019-07-20 | 1 | 100 | Print of the screen layouts | High | Phase 4
2.2.5 Error Logs | P.Hoben | 2019-07-18 | 2019-07-20 | 2 | 100 | Error logs | High | Phase 4
2.3 External Documentation | P.Hoben | 2019-07-15 | 2019-07-19 | 4 | 100 |  | High | Phase 5
2.3.1 User Manual | P.Hoben | 2019-07-28 | 2019-08-12 | 15 | 0 | Completion of a user manual | High | Phase 5
2.3.2 Installation Guide | P.Hoben | 2019-07-15 | 2019-07-16 | 1 | 100 | Create an installation guide | High | Phase 5
2.3.3 Updated Gantt Chart | P.Hoben | 2019-07-18 | 2019-07-19 | 1 | 100 | The Gantt chart is to be updated at this stage | High | Phase 5
Stage 3: Evaluation | P.Hoben | 2019-07-19 | 2019-08-12 | 24 | 100 |  | High | Phase 6
3.1 Outline Of the Assignment | P.Hoben | 2019-07-23 | 2019-08-12 | 20 | 100 | Outline the assignment | High | Phase 6
3.2 Strengths and Weaknesses | P.Hoben | 2019-07-24 | 2019-08-12 | 19 | 100 | Stengths and weakeness encountered during the project | High | Phase 6
3.3 Modifications | P.Hoben | 2019-07-25 | 2019-08-12 | 18 | 100 | List of any modifcations I would have done | High | Phase 6
3.4 Knowledge and Skills | P.Hoben | 2019-07-26 | 2019-08-12 | 17 | 100 | What Knowledge and skills used and also gained during the project | High | Phase 6
3.5 Recommendations | P.Hoben | 2019-07-28 | 2019-08-12 | 15 | 100 | recommendations for undertaking a similar project in the future | High | Phase 6

## Coding Tasks(inprogress)
Allswell Hospital
PHOBENS
P.Hoben
TASK NAME | ASSIGNED TO | START DATE | DUE DATE | DURATION | % DONE | DESCRIPTION | PRIORITY | SPRINT/MILESTONE
Start of Planning Phase |  |  |  | 0
1.1 Initial Planning
Prepare Requirement Spec Document | P.Hoben | 2019-03-11 | 2019-06-14 | 95 | 100 | from the clients specification, create a req spec of what is required on the system |  | Phase 1
Prepare Detailed Requirements Document | P.Hoben | 2019-03-11 | 2019-06-14 | 95 | 100 | detailed req docs should be producted |  | Phase 1
Prepare questionaires | P.Hoben | 2019-03-15 | 2019-03-22 | 7 | 100 | Prepare a list of interview questions to be issued |  | Phase 1
Analysis Interview Questions | P.Hoben | 2019-03-23 | 2019-03-25 | 2 | 100 | Extract Info from the Intervierw questions to help develop requirments spec.
Planning report | P.Hoben | 2019-03-15 | 2019-04-15 | 31 | 100 |  |  | Phase 1
Prepare A Project Timeline | P.Hoben | 2019-04-17 | 2019-04-18 | 1 | 100 | Prepare a Gantt hart for the project |  | Phase 1
End of Phase 1 Planning |  |  | 2019-06-14 | 43630 | 100 | Mile Stone for Phase 1 completed
Prepare Screen Layouts/Story Boards | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 2
Prepare OverView of Site Functions Report | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 2
Prepare Use Case Diagram | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 2
Prepare a Class Diagram | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 2
Prepare Data Dictionary | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 2
Prepare Module Description Documents | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 2
Prepare Event handling Forms | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 2
Prepare test Cases | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 2
Prepare Test Data with expected Results | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 2
End of Phase 2 Development |  |  | 2019-06-14 | 43630 | 0 | Mile Stone for Phase 2 Completed
Use responsive design principles to target a range of platforms and devices. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Use control structures and modularity. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Use client and server based objects. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Code is commented appropriately. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Use a dialogue box. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Include client side validation of registration form. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Use POST or GET in forms. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Use custom handlers of touch events. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Use custom window and document events. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Use custom handlers of change events. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Use custom handlers of key events. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Use custom handlers of button events. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Use custom handlers of submit events. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Includes setting and retrieving of data in cookies. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Suitable security measures implemented (password encryption, login handling, prepared statements). | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Read data from a database. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Insert data into a database. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Delete data from a database. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Update data in a database | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Provide test document with expected results, actual results and action taken. | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
Test logs | P.Hoben |  | 2019-06-14 | 43630 | 0 |  |  | Phase 3
End of phase 3 Evaluation |  |  |  | 0 | 0
Extra |  |  |  |  | 0 |  |  | Phase 3

## Sheet2
Start of Planning Phase
1.1 Initial Planning |  | 1.1.2
Prepare Requirement Spec Document |  | Interpretaion of the project assignment
Prepare Detailed Requirements Document |  | Initial functional and non funcational requirements
Prepare questionaires |  | initial top level use case model
Planning report |  | initial class diagram
Prepare A Project Timeline |  | information gathered to clarify the brief
1.2 Analysis and Design |  | aims of the project
End of Phase 1 Planning |  | identification of the resourese identification
Prepare Screen Layouts/Story Boards |  | 1.13
Prepare OverView of Site Functions Report |  | Main Milestones (Implementation, testing etc) (1)
Prepare Use Case Diagram |  | Breakdown of tasks in each stage (1)
Prepare a Class Diagram |  | Realistic timescales (for each task) (1)
Prepare Data Dictionary |  | Scheduling of tasks (1)
Prepare Module Description Documents |  | Deliverable (1)
Prepare Event handling Forms |  | Resources used (1)
Prepare test Cases
Prepare Test Data with expected Results
End of Phase 2 Development | 4 weeks | Stage 1.2
Use responsive design principles to target a range of platforms and devices. |  | Use case diagrams – in-depth for two functions Place an order/Make a booking AND another of your choice (2)
Use control structures and modularity. |  | Class Diagram-detailed (2)
Use client and server based objects. |  | Activity Diagrams – for two functions Place an order/Make a booking AND another of your choice (2)
Code is commented appropriately. |  | Sequence Diagrams- for two functions Place an order/Make a booking AND another of your choice (2)
Use a dialogue box. |  | Normalization (2)
Include client side validation of registration form. |  | ER Diagram (2)
Use POST or GET in forms. |  | Event Handling Forms (2 forms) – for two functions Place an order/Make a booking AND another of your choice (2)
Use custom handlers of touch events. |  | Module Description (2 forms) (2)
Use custom window and document events. |  | Screen Layouts Charts (for each completed form/web page) (4)
Use custom handlers of change events.
Use custom handlers of key events. |  | stage 2
Use custom handlers of button events. |  | 2.1
Use custom handlers of submit events. |  | Business Model Code Listings- implementation of the problem domain. (5) View Model Code Listings-implementation of the UI domain. (5) Use of unfamiliar libraries and/or constructs (5) Error handling- use of exceptions, and/or validation methods. (5) Internal Documentation- comments (eg using XML documentation in Visual Studio or JavaDoc in Eclipse), naming conventions and appropriate use of indentation. (5)
Includes setting and retrieving of data in cookies.
Suitable security measures implemented (password encryption, login handling, prepared statements).
Read data from a database.
Insert data into a database.
Delete data from a database.
Update data in a database
Provide test document with expected results, actual results and action taken.
Test logs
End of phase 3 Evaluation
Extra